


SECTION 01150
INSTRUCTIONS TO PROPOSERS
MOBLEY PARK REMODEL
DESIGN-BUILD REQUEST FOR PROPOSALS
1.1 PURPOSE
The City of Port Wentworth, Georgia ("City") is soliciting sealed proposals from qualified Design-Build Teams for the design, permitting, and construction of the Mobley Park Remodel Project located at the 400 Block of Armadale Road, Port Wentworth, Georgia 31407.
The City intends to utilize a Design-Build delivery method whereby the selected proposer shall provide all professional services, labor, materials, supervision, equipment, permitting, and incidentals necessary to complete the project.
1.2 PROCUREMENT SCHEDULE
Advertisement of RFP: October 5th, 2026
Mandatory Pre-Proposal Meeting:
October 14, 2026
11:00 A.M. EST
Port Wentworth City Hall
7224 Highway 21
Port Wentworth, Georgia 31407
Deadline for Written Questions:
October 23, 2026
Addenda Issued:
October 30, 2026
Proposal Submission Deadline:
November 13, 2026
11:00 A.M. EST
Anticipated Award:
No Later Than November 24, 2026
Notice to Proceed:
Within Thirty (30) Days of Award
1.3 PROPOSAL SUBMISSION
Proposals shall be submitted in a sealed envelope clearly marked:
"MOBLEY PARK REMODEL
DESIGN-BUILD REQUEST FOR PROPOSALS"
Proposals shall be delivered to:
City of Port Wentworth
Attn: David Stahl, Deputy City Manager
7224 Highway 21
Port Wentworth, Georgia 31407
Late proposals shall not be accepted.
The City shall not be responsible for delays caused by mail carriers, delivery services, or other circumstances beyond its control.
1.4 MANDATORY PRE-PROPOSAL MEETING
Attendance at the pre-proposal meeting is mandatory.
Any proposer not represented at the mandatory pre-proposal meeting shall be deemed non-responsive and shall not be considered for award.
1.5 QUESTIONS AND INTERPRETATIONS
Questions concerning this solicitation shall be submitted in writing.
Questions must be received no later than the date identified in the Procurement Schedule.
Only written addenda issued by the City shall be binding.
Verbal interpretations, comments, or clarifications shall not be binding.
1.6 EXAMINATION OF SITE
Each proposer shall visit the project site and become familiar with existing conditions.
Failure to inspect the site shall not relieve the proposer from performing the work required under the contract.
The City makes no representation regarding existing conditions beyond information contained within the solicitation documents.
1.7 ERRORS, OMISSIONS, AND DISCREPANCIES
Proposers shall immediately notify the City of any ambiguity, discrepancy, conflict, or omission identified within the solicitation documents.
Failure to provide such notice shall constitute acceptance of the documents as issued.
1.8 WITHDRAWAL OF PROPOSALS
A proposal may be withdrawn prior to the submission deadline through written notice submitted by an authorized representative.
After the proposal deadline, proposals shall remain valid for ninety (90) calendar days.
1.9 RIGHT TO REJECT
The City reserves the right to:
Reject any or all proposals.
Waive informalities and irregularities.
Request clarification of proposal information.
Negotiate with one or more proposers.
Cancel the solicitation.
Reissue the solicitation.
Award in the best interest of the City.
1.10 DESIGN-BUILD TEAM REQUIREMENTS
Each proposer shall identify a Design-Build Team consisting of:
Georgia Licensed General Contractor.
Georgia Registered Architect.
Georgia Licensed Professional Engineer.
Additional consultants required to complete the project.
The Design-Build Team shall remain substantially intact throughout the duration of the project unless approved by the City.
1.11 MINIMUM QUALIFICATIONS
Proposers shall demonstrate:
Experience completing similar parks and recreation projects.
Experience utilizing Design-Build delivery methods.
Financial capability to complete the project.
Acceptable safety record.
Acceptable references.
No debarment by any governmental agency.
1.12 PROPOSAL FORMAT
Proposals shall include the following sections:
A. Cover Letter
B. Company Background
C. Design-Build Team Information
D. Relevant Project Experience
E. Project Approach
F. Preliminary Design Narrative
G. Preliminary Schedule
H. Safety Information
I. Financial Information
J. References
K. Fee Proposal
L. Required Certifications
1.13 COMPANY BACKGROUND
Provide:
Legal business name.
Business address.
Years in business.
Ownership information.
Corporate structure.
Primary point of contact.
Georgia contractor license information.
1.14 DESIGN-BUILD TEAM INFORMATION
Identify:
General Contractor.
Architect of Record.
Engineer of Record.
Key personnel.
Project manager.
Construction superintendent.
Provide resumes for key personnel.
1.15 RELEVANT EXPERIENCE
Provide descriptions of at least five (5) comparable projects completed within the previous ten (10) years.
Include:
Project name.
Location.
Contract value.
Owner.
Delivery method.
Completion date.
Reference information.
1.16 PRELIMINARY DESIGN NARRATIVE
Provide a narrative describing the proposed approach for:
Site improvements.
Athletic field improvements.
Irrigation systems.
Building renovations.
Architectural treatments.
Electrical upgrades.
Construction sequencing.
Public safety considerations.
1.17 PRELIMINARY PROJECT SCHEDULE
Provide a schedule demonstrating completion within one hundred eighty (180) calendar days following Notice to Proceed.
The schedule shall identify:
Design phase.
Permitting phase.
Procurement phase.
Construction phase.
Substantial Completion.
Final Completion.
1.18 FINANCIAL INFORMATION
Provide:
Financial references.
Evidence of bonding capacity.
Pending litigation.
Bank references.
Surety information.
1.19 SAFETY INFORMATION
Provide:
EMR for the previous three years.
OSHA citations within the previous five years.
Written safety program.
Recordable incident rates.
1.20 REFERENCES
Provide a minimum of five owner references for comparable projects.
The City reserves the right to contact references.
1.21 FEE PROPOSAL
Provide a separate fee proposal including:
Lump Sum Price.
Design Services Cost.
Construction Cost.
General Conditions.
Contingency.
The City reserves the right to negotiate pricing.
1.22 EVALUATION PROCESS
Proposals shall be evaluated using the scoring method below:
Bid Form:
Up to 5 Points
Statement of Qualifications:
Up to 30 Points
Company Background and Approach:
Up to 10 Points
Litigation, Financial Information and Safety:
Up to 5 Points
Lump Sum Price:
Up to 50 Points
1.23 INTERVIEWS
The City reserves the right to conduct interviews with one or more proposers.
1.24 NEGOTIATION
The City reserves the right to negotiate scope, schedule, fee, staffing, and contract terms with the highest-ranked proposer.
1.25 DESIGN REVIEW PROCESS
The selected proposer shall submit a Conceptual Design Package within thirty (30) calendar days of Notice to Proceed.
The Conceptual Design Package shall include:
Site plan.
Architectural elevations.
Material selections.
Preliminary irrigation layout.
Construction schedule.
The City Manager shall serve as the approving authority for conceptual design submissions.
No final design work shall proceed until conceptual approval is received.
1.26 PERMITS
The Design-Build Team shall obtain all permits required for the project.
1.27 BONDS
The successful proposer shall provide:
Bid Bond equal to five percent (5%) of the proposal amount.
Performance Bond equal to one hundred percent (100%) of the contract value.
Payment Bond equal to one hundred percent (100%) of the contract value.
1.28 INSURANCE
The successful proposer shall maintain insurance coverage consistent with City requirements and Georgia law.
1.29 LIQUIDATED DAMAGES
Liquidated damages shall be assessed at Five Hundred Dollars ($500.00) per calendar day for failure to achieve Substantial Completion within the contract time.
1.30 GOVERNING LAW
This procurement and resulting agreement shall be governed by the laws of the State of Georgia.
Venue for any legal action shall lie in Chatham County, Georgia.




















SECTION 01160
GENERAL CONDITIONS
MOBLEY PARK REMODEL
DESIGN-BUILD REQUEST FOR PROPOSALS
2.1 GENERAL
These General Conditions shall govern the obligations, responsibilities, and rights of the City of Port Wentworth ("Owner") and the selected Design-Build Team ("Contractor") for the Mobley Park Remodel Project.
These General Conditions shall become part of the resulting Design-Build Agreement.
2.2 CONTRACT DOCUMENTS
The Contract Documents shall consist of:
• Request for Proposals
• Addenda
• Contractor's Proposal
• Design-Build Agreement
• Performance Bond
• Payment Bond
• Notice to Proceed
• Approved Change Orders
• Approved Design Documents
• Approved Submittals
• Supplemental Conditions
• General Conditions
• Technical Specifications
• Any documents incorporated by reference
In the event of a conflict between Contract Documents, the more stringent requirement shall govern unless otherwise directed by the Owner.
2.3 CONTRACTOR RESPONSIBILITY
The Contractor shall provide all labor, supervision, professional services, materials, equipment, tools, permits, transportation, insurance, bonds, and incidentals necessary to complete the Work.
The Contractor shall coordinate all activities associated with the project.
The Contractor shall be solely responsible for means, methods, techniques, sequences, and procedures of construction.
2.4 DESIGN RESPONSIBILITY
The Contractor shall retain all necessary licensed design professionals required to complete the project.
All design documents shall be prepared under the supervision of professionals licensed in the State of Georgia.
The Contractor shall be responsible for the accuracy and completeness of all design documents.
Review by the Owner shall not relieve the Contractor of design responsibility.
2.5 STANDARD OF CARE
The Contractor shall perform all services in accordance with the degree of care and skill ordinarily exercised by qualified professionals performing similar services under similar conditions.
2.6 PROJECT MANAGER
The Contractor shall designate a Project Manager authorized to act on behalf of the Contractor.
The Project Manager shall remain assigned to the project unless replacement is approved by the Owner.
2.7 SUPERINTENDENT
The Contractor shall maintain a qualified superintendent on-site whenever construction activities are underway.
The superintendent shall have authority to direct the Work.
2.8 SUBCONTRACTORS
The Contractor shall be fully responsible for all subcontractors.
No subcontract shall relieve the Contractor of obligations under the Contract.
The Owner reserves the right to reject any subcontractor for reasonable cause.
2.9 PERMITS AND LICENSES
The Contractor shall obtain all permits, approvals, inspections, licenses, and certifications required for completion of the Work.
Permit fees shall be included within the Contract Price unless specifically exempted by law.
2.10 COMPLIANCE WITH LAWS
The Contractor shall comply with all applicable federal, state, county, and local laws, regulations, codes, ordinances, and standards.
Applicable requirements include but are not limited to:
• Georgia State Minimum Standard Codes
• OSHA Requirements
• ADA Requirements
• Georgia Erosion and Sedimentation Act
• Georgia Immigration Compliance Act
• Georgia Open Records Act
• Chatham County Regulations
• City of Port Wentworth Ordinances
2.11 SAFETY
The Contractor shall be solely responsible for jobsite safety.
The Contractor shall establish and maintain safety programs sufficient to protect:
• Employees
• Visitors
• City Personnel
• Park Users
• Adjacent Property Owners
The Contractor shall immediately correct unsafe conditions.
2.12 PROTECTION OF PROPERTY
The Contractor shall protect existing improvements, utilities, buildings, fields, scoreboards, lighting systems, landscaping, and adjacent property.
Damage caused by the Contractor shall be repaired at no cost to the Owner.
2.13 UTILITIES
The Contractor shall verify utility locations before commencing work.
The Contractor shall coordinate utility conflicts with utility providers.
The Owner does not guarantee the accuracy of utility information.
2.14 WORK HOURS
Normal construction operations shall occur between 7:00 A.M. and 7:00 P.M. unless otherwise approved by the Owner.
Work outside normal hours may require prior approval.
2.15 SUBMITTALS
The Contractor shall submit all required:
• Shop Drawings
• Product Data
• Material Samples
• Color Selections
• Design Documents
• Engineering Calculations
Work requiring submittals shall not proceed until reviewed.
2.16 OWNER REVIEW
Owner review shall be for general conformance with project requirements.
Review shall not relieve the Contractor from responsibility for:
• Errors
• Omissions
• Quantities
• Dimensions
• Design Compliance
• Code Compliance
2.17 CHANGES IN THE WORK
The Owner may order changes in the Work.
Changes may be accomplished through:
• Change Order
• Construction Change Directive
• Field Directive
No adjustment to Contract Price or Contract Time shall occur without written authorization.
2.18 DIFFERING SITE CONDITIONS
The Contractor shall immediately notify the Owner upon discovery of concealed or unknown conditions materially differing from those ordinarily encountered.
The Owner shall investigate and determine appropriate action.
2.19 PAYMENT APPLICATIONS
The Contractor shall submit monthly payment applications.
Applications shall include:
• Schedule of Values
• Percentage Complete
• Stored Materials Documentation
• Lien Waivers
• Supporting Documentation
The Owner shall review payment applications and process payment in accordance with Georgia law.
2.20 RETAINAGE
The Owner may withhold retainage as permitted by Georgia law.
Retainage may be reduced or released upon satisfactory progress.
2.21 DEFECTIVE WORK
Work not conforming to Contract requirements shall be considered defective.
The Owner may require correction, replacement, or removal of defective work.
All corrective work shall be performed at no cost to the Owner.
2.22 SUBSTANTIAL COMPLETION
Substantial Completion shall occur when the Work is sufficiently complete for intended use.
The Contractor shall request inspection when substantial completion is achieved.
Substantial Completion for this project shall occur within one hundred eighty (180) calendar days following Notice to Proceed.
2.23 FINAL COMPLETION
Final Completion shall occur within thirty (30) calendar days following Substantial Completion.
Requirements include:
• Completion of Punch List
• Delivery of Warranties
• Delivery of As-Builts
• Final Lien Waivers
• Final Closeout Documents
2.24 LIQUIDATED DAMAGES
Time is of the essence.
If Substantial Completion is not achieved within the Contract Time, the Contractor shall pay liquidated damages of Five Hundred Dollars ($500.00) per calendar day.
Liquidated damages are intended to compensate the Owner for administrative and operational impacts resulting from delayed completion.
2.25 INSURANCE
The Contractor shall maintain insurance throughout the duration of the project.
Minimum insurance limits shall be:
Commercial General Liability:
$1,000,000 Per Occurrence
$2,000,000 Aggregate
Automobile Liability:
$1,000,000 Combined Single Limit
Workers Compensation:
Statutory Limits
Employer's Liability:
$1,000,000
Professional Liability:
$1,000,000
Builder's Risk:
Full Replacement Value
The City of Port Wentworth shall be named as Additional Insured where applicable.
2.26 PERFORMANCE BOND
The Contractor shall provide a Performance Bond equal to one hundred percent (100%) of the Contract Amount.
2.27 PAYMENT BOND
The Contractor shall provide a Payment Bond equal to one hundred percent (100%) of the Contract Amount.
2.28 INDEMNIFICATION
To the fullest extent permitted by law, the Contractor shall indemnify, defend, and hold harmless the City of Port Wentworth, its elected officials, officers, employees, agents, and representatives from claims, damages, losses, liabilities, and expenses arising from performance of the Work.
2.29 DEFAULT
The Contractor shall be in default if the Contractor:
• Fails to supply sufficient labor
• Fails to supply sufficient materials
• Fails to maintain project schedule
• Violates applicable laws
• Fails to comply with Contract requirements
• Becomes insolvent
• Abandons the Work
2.30 TERMINATION FOR CAUSE
Upon Contractor default, the Owner may terminate the Contract after providing written notice and opportunity to cure.
The Owner may complete the Work through others and recover associated costs.
2.31 TERMINATION FOR CONVENIENCE
The Owner reserves the right to terminate the Contract for convenience.
The Contractor shall be compensated for Work properly completed through the termination date.
2.32 DISPUTE RESOLUTION
The parties shall first attempt to resolve disputes through informal negotiations.
If unresolved, disputes shall be subject to mediation before litigation.
2.33 GOVERNING LAW
The Contract shall be governed by the laws of the State of Georgia.
Venue shall be exclusively in Chatham County, Georgia.
2.34 OPEN RECORDS
The Contractor acknowledges that project records may be subject to the Georgia Open Records Act.
2.35 WARRANTY
The Contractor shall provide a minimum one-year warranty on all labor, materials, equipment, workmanship, and installed systems.
Warranty periods shall begin upon Final Acceptance by the Owner.
END OF SECTION 01160



SECTION 01200
SUPPLEMENTAL CONDITIONS
MOBLEY PARK REMODEL
DESIGN-BUILD REQUEST FOR PROPOSALS
3.1 PURPOSE
These Supplemental Conditions modify and supplement the General Conditions and shall govern the specific requirements associated with the Mobley Park Remodel Project.
Where a conflict exists between the General Conditions and Supplemental Conditions, the Supplemental Conditions shall govern.
3.2 PROJECT DESCRIPTION
The project consists of the design, permitting, and construction associated with the renovation and modernization of Mobley Park located at the 400 Block of Armadale Road, Port Wentworth, Georgia 31407.
The project includes improvements to:
• Athletic Facilities
• Building Facilities
• Irrigation Systems
• Sidewalk Systems
• Electrical Infrastructure
• Site Improvements
The project shall be delivered utilizing a Design-Build procurement method.
3.3 DESIGN-BUILD DELIVERY
The Design-Build Team shall be responsible for:
• Architectural Design
• Civil Engineering
• Structural Engineering
• Mechanical Engineering
• Electrical Engineering
• Plumbing Engineering
• Irrigation Design
• Permitting
• Construction Administration
• Construction
• Project Closeout
The Design-Build Team shall provide all professional services necessary to deliver a complete and functional project.
3.4 EXISTING CONDITIONS
No architectural, engineering, irrigation, grading, structural, or construction documents currently exist for the proposed improvements.
The Contractor shall verify all existing conditions.
The Contractor shall field verify:
• Dimensions
• Elevations
• Utilities
• Existing Structures
• Existing Infrastructure
The Contractor shall not rely solely upon aerial photography, verbal information, or assumptions.
3.5 DESIGN PHASE REQUIREMENTS
The Design Build Team shall prepare all design documents required to construct the project.
All design documents shall be prepared under the supervision of Georgia licensed professionals.
The Design-Build Team shall provide:
• Site Plans
• Grading Plans
• Drainage Plans
• Irrigation Plans
• Architectural Plans
• Structural Plans
• Mechanical Plans
• Electrical Plans
• Plumbing Plans
• Technical Specifications
3.6 CONCEPTUAL DESIGN SUBMITTAL
Within thirty (30) calendar days of Notice to Proceed, the Design-Build Team shall submit a Conceptual Design Package.
The Conceptual Design Package shall include:
• Preliminary Site Plan
• Preliminary Architectural Elevations
• Preliminary Material Selections
• Preliminary Irrigation Layout
• Preliminary Grading Concept
• Preliminary Construction Schedule
• Preliminary Phasing Plan
The purpose of the Conceptual Design Package is to establish project direction before final design development.
3.7 CITY MANAGER REVIEW
The City Manager shall serve as the approving authority for Conceptual Design submissions.
The Design-Build Team shall not proceed into final design until Conceptual Design approval is obtained.
The City Manager may require revisions to:
• Layout
• Materials
• Colors
• Architectural Features
• Site Improvements
• Building Improvements
The Design-Build Team shall incorporate approved revisions without additional compensation unless the revisions materially alter the approved scope.
3.8 FINAL DESIGN SUBMITTAL
Following Conceptual Design approval, the Design-Build Team shall prepare final construction documents.
Final construction documents shall be suitable for permitting, bidding of subcontractors, and construction.
All final documents shall bear the seal of the appropriate Georgia licensed design professional.
3.9 PERMITTING
The Design-Build Team shall obtain all permits necessary for completion of the project.
Required permits may include:
• Building Permits
• Electrical Permits
• Plumbing Permits
• Mechanical Permits
• Land Disturbance Permits
• Erosion Control Permits
• Utility Permits
The Contractor shall coordinate all inspections.
3.10 PROJECT SCHEDULE
The Contractor shall maintain a detailed project schedule throughout the duration of the project.
The schedule shall include:
• Design Activities
• Permitting Activities
• Procurement Activities
• Construction Activities
• Substantial Completion
• Final Completion
Updated schedules shall be provided monthly.
3.11 SUBSTANTIAL COMPLETION
Substantial Completion shall be achieved within one hundred eighty (180) calendar days following issuance of the Notice to Proceed.
The Design-Build Team shall include sufficient staffing and resources to achieve the required completion date.
3.12 FINAL COMPLETION
Final Completion shall occur within thirty (30) calendar days following Substantial Completion.
Final Completion requirements include:
• Completion of Punch List Items
• Delivery of As-Built Drawings
• Delivery of Warranties
• Delivery of Operations Manuals
• Final Site Cleanup
3.13 ARCHITECTURAL CONSISTENCY
The Design-Build Team shall maintain a consistent architectural theme throughout the project.
The Restroom Building, Announcer Building, and Concession Building shall incorporate:
• Similar Architectural Character
• Coordinated Roofing Systems
• Coordinated Exterior Finishes
• Coordinated Colors
• Coordinated Materials
• Coordinated Architectural Features
The intent is to create a cohesive appearance throughout the park.
3.14 BUILDING MATERIALS
Exterior building renovations shall incorporate:
• Stone Veneer
• Earth Tone Finishes
• Durable Commercial Materials
• Weather Resistant Finishes
Material selections shall be submitted to the Deputy City Manager for approval.
3.15 IRRIGATION DESIGN
The Contractor shall prepare complete irrigation designs for:
• Existing Football Field
• Baseball Field No. 1 Outfield
• Baseball Field No. 2 Outfield
• Baseball Field No. 3 Outfield
The Contractor shall determine:
• Number of Zones
• Head Locations
• Pipe Sizes
• Controllers
• Water Requirements
• Backflow Prevention
The irrigation system shall provide complete and uniform coverage.
3.16 ATHLETIC FIELD DESIGN
The Contractor shall evaluate existing field conditions and prepare grading and drainage improvements necessary to improve playability.
The Design-Build Team shall prepare engineering calculations supporting the proposed grading approach.
All drainage shall direct water away from playing surfaces.
3.17 BATTING CAGE DESIGN
The batting cage facility shall be designed and constructed in accordance with applicable codes.
The structure shall include:
• Reinforced Concrete Foundation
• Structural Framing
• Protective Netting
• Divider Netting
• Two Twelve-Foot Batting Lanes
3.18 ELECTRICAL INVESTIGATION
The Contractor shall investigate existing electrical infrastructure throughout the park.
Deficiencies identified shall be corrected.
The Contractor shall provide documentation of corrective actions.
3.19 EXISTING FACILITIES
Existing scoreboards shall remain in place.
Existing field lighting shall remain in place.
The Contractor shall protect these facilities during construction.
Any damage shall be repaired at the Contractor's expense.
3.20 EXCLUDED WORK
The following items are specifically excluded from the project:
• Parking Lot Improvements
• Playground Improvements
• Security Camera Systems
• Access Control Systems
• Public Wi-Fi Systems
• Audiovisual Systems
• Scoreboard Replacement
• Athletic Lighting Replacement
3.21 PUBLIC ACCESS
The Contractor shall coordinate construction activities to minimize disruption to park operations whenever feasible.
The Contractor shall maintain safe access for authorized personnel.
3.22 CONSTRUCTION STAGING
The Contractor shall submit a staging plan for Owner review.
The staging plan shall identify:
• Material Storage Areas
• Equipment Storage Areas
• Temporary Fencing
• Safety Controls
• Construction Access Routes
3.23 AS-BUILT DOCUMENTS
The Contractor shall maintain current redline drawings throughout construction.
Upon completion, the Contractor shall provide:
• One Electronic PDF Set
• One Electronic CAD Set, if available
• Final Record Drawings
3.24 WARRANTY PERIOD
The warranty period shall commence upon Final Acceptance.
The minimum warranty period shall be one (1) year.
Manufacturer warranties exceeding one year shall be assigned to the Owner.
3.25 LIQUIDATED DAMAGES
Failure to achieve Substantial Completion within the Contract Time shall result in liquidated damages of Five Hundred Dollars ($500.00) per calendar day.
3.26 PROJECT CLOSEOUT
Prior to Final Acceptance, the Contractor shall provide:
• Final Lien Waivers
• Warranty Documentation
• As-Built Drawings
• Operations Manuals
• Maintenance Manuals
• Final Inspection Reports
• Certificate of Occupancy, if applicable
END OF SECTION 01200



SECTION 01210
SCOPE OF WORK
MOBLEY PARK REMODEL
DESIGN-BUILD REQUEST FOR PROPOSALS
4.1 GENERAL
The Design-Build Team shall furnish all labor, supervision, professional services, engineering, architecture, permitting, equipment, materials, tools, transportation, utilities, testing, inspections, and incidentals necessary to complete the Mobley Park Remodel Project.
The project is intended to modernize and improve the functionality, appearance, safety, and long-term maintainability of Mobley Park.
The Design-Build Team shall provide a complete and fully operational project ready for public use.
4.2 PROJECT LOCATION
Mobley Park
400 Block Armadale Road
Port Wentworth, Georgia 31407
4.3 DESIGN-BUILD SERVICES
The Design-Build Team shall provide:
• Architectural Design
• Civil Engineering
• Structural Engineering
• Mechanical Engineering
• Electrical Engineering
• Plumbing Engineering
• Irrigation Design
• Permitting Services
• Construction Administration
• Construction Services
• Project Closeout Services
The Design-Build Team shall verify all existing conditions and dimensions prior to commencement of design.
4.4 SITE IMPROVEMENTS
The Contractor shall remove and replace all existing concrete sidewalks and pedestrian walkways throughout the project area.
New sidewalks shall:
• Be six feet (6') in width.
• Be constructed of reinforced concrete.
• Meet current ADA accessibility requirements.
• Provide positive drainage.
• Connect all major park facilities.
The Contractor shall extend concrete paving around all existing buildings.
Building paving extensions shall:
• Extend ten feet (10') from all building faces.
• Tie into the sidewalk system.
• Provide positive drainage away from structures.
• Match adjacent concrete finishes.
All disturbed areas shall be restored.
4.5 ATHLETIC FIELD IMPROVEMENTS
The Contractor shall renovate all three baseball fields.
Work shall include:
• Infield reconstruction.
• Regrading.
• Drainage improvements.
• Dugout improvements.
• Fence replacement.
The objective is to provide safe, playable, and maintainable athletic facilities.
4.6 INFIELD RECONSTRUCTION
The Contractor shall reconstruct all infield areas.
Work shall include:
• Removal of unsuitable materials.
• Fine grading.
• Laser grading, if proposed.
• Establishment of proper playing elevations.
• Positive drainage.
The Contractor shall evaluate existing conditions and determine the most appropriate reconstruction method.
Finished grades shall prevent ponding and standing water.
4.7 FIELD DRAINAGE
The Contractor shall design and construct drainage improvements necessary to improve field performance.
Drainage improvements may include:
• Surface grading.
• Swales.
• Drainage structures.
• Underdrain systems.
• Other drainage improvements proposed by the Design-Build Team.
The Contractor shall provide engineering calculations supporting the drainage design.
4.8 DUGOUT IMPROVEMENTS
The Contractor shall renovate or reconstruct existing dugouts as required to coordinate with field improvements.
The final design shall:
• Improve functionality.
• Improve durability.
• Coordinate with field renovations.
• Coordinate with fence improvements.
Materials shall be durable and suitable for athletic facility use.
4.9 FIELD FENCING
The Contractor shall remove and replace existing fencing associated with the baseball facilities.
The Contractor shall provide:
• Chain-link fencing.
• Gates.
• Hardware.
• Backstop improvements.
• Protective fencing.
Fence systems shall be designed for long-term athletic use.
All fencing shall comply with applicable codes.
4.10 OUTFIELDS
Existing outfields shall remain in place.
The outfields are not included in the grading or reconstruction scope.
The only improvements to the outfields shall be irrigation installation.
4.11 FOOTBALL FIELD
The existing football field shall remain in place.
The football field shall receive irrigation improvements only.
No grading or reconstruction of the football field is required.
4.12 IRRIGATION SYSTEMS
The Contractor shall design and install complete irrigation systems serving:
• Existing Football Field.
• Baseball Field No. 1 Outfield.
• Baseball Field No. 2 Outfield.
• Baseball Field No. 3 Outfield.
The Contractor shall connect to the existing water meter.
The Contractor shall determine:
• Number of zones.
• Head locations.
• Controller locations.
• Pipe sizing.
• Valve locations.
• Water demand.
• Backflow prevention.
The irrigation system shall provide complete and uniform coverage.
4.13 IRRIGATION CONTROLS
The Contractor shall provide a programmable irrigation control system.
The system shall be:
• Commercial grade.
• Easily maintainable.
• Weather resistant.
The Contractor shall provide owner training upon completion.
4.14 BATTING CAGE FACILITY
The Contractor shall demolish and remove the existing batting cage structure.
The Contractor shall design and construct a replacement batting cage facility.
4.15 BATTING CAGE REQUIREMENTS
The new facility shall include:
Overall Dimensions:
24 feet wide by 55 feet long.
Batting Lanes:
Two (2) lanes.
Lane Width:
12 feet each.
The facility shall include:
• Reinforced concrete slab.
• Structural support framing.
• Protective netting.
• Divider netting.
• Code-compliant construction.
All structural components shall be designed by a Georgia licensed engineer.
4.16 RESTROOM BUILDING
The existing restroom building shall be renovated.
The renovation shall include both exterior and interior improvements.
4.17 RESTROOM BUILDING EXTERIOR
The Contractor shall:
• Remove and replace roofing system.
• Install stone veneer.
• Install earth-tone finishes.
• Repair exterior deficiencies.
• Replace damaged exterior materials.
The completed building shall coordinate architecturally with all other renovated structures.
4.18 RESTROOM BUILDING INTERIOR
The Contractor shall completely renovate the interior.
Improvements shall include:
• New sheetrock.
• New paint.
• New lighting.
• New plumbing fixtures.
• New toilets.
• New sinks.
• New accessories.
• New finishes.
The Contractor shall replace components as necessary to provide a complete and functional facility.
4.19 RESTROOM HVAC
The Contractor shall provide split-system HVAC units serving the men's and women's restroom areas.
Systems shall be sized by a licensed mechanical engineer.
4.20 ANNOUNCER BUILDING
The existing announcer building shall be renovated.
4.21 ANNOUNCER BUILDING EXTERIOR
The Contractor shall:
• Remove and replace roofing.
• Install stone veneer.
• Install earth-tone finishes.
• Coordinate architecture with the restroom and concession buildings.
4.22 ANNOUNCER BUILDING INTERIOR
The Contractor shall renovate the second-floor interior.
Improvements shall include:
• New sheetrock.
• New ceilings.
• New lighting.
• New finishes.
4.23 ANNOUNCER BUILDING STAIR ACCESS
The existing interior stair access shall be removed.
The Contractor shall construct a new exterior stair system on the rear side of the building.
The stair system shall comply with applicable codes.
4.24 ANNOUNCER BUILDING HVAC
The Contractor shall provide a split-system HVAC unit serving the second floor.
4.25 CONCESSION BUILDING
The concession building shall be fully renovated.
4.26 CONCESSION BUILDING EXTERIOR
The Contractor shall:
• Remove and replace roofing.
• Install stone veneer.
• Install earth-tone finishes.
• Coordinate architecture with all renovated structures.
4.27 CONCESSION BUILDING INTERIOR
The Contractor shall provide:
• New sheetrock.
• New ceilings.
• New flooring.
• New countertops.
• New windows.
• New lighting.
• New plumbing fixtures.
• New finishes.
4.28 COMMERCIAL KITCHEN EQUIPMENT
The Contractor shall provide commercial-grade equipment suitable for public recreation facility operations.
The Contractor shall provide equipment recommendations as part of final design.
4.29 SERVICE WINDOW
The primary concession service window shall include a lockable roll-up security cover.
The cover shall be designed for durability and security.
4.30 CONCESSION HVAC
The Contractor shall provide split-system HVAC equipment serving the concession facility.
4.31 ARCHITECTURAL CONSISTENCY
The restroom building, announcer building, and concession building shall utilize a unified architectural theme.
The buildings shall incorporate:
• Similar roof systems.
• Similar colors.
• Similar materials.
• Similar architectural treatments.
• Similar stone veneer applications.
The objective is to create a cohesive park appearance.
4.32 ELECTRICAL SYSTEMS
The Contractor shall evaluate all existing electrical infrastructure throughout the park.
The Contractor shall identify deficiencies and bring systems into compliance with applicable codes.
4.33 ELECTRICAL IMPROVEMENTS
Work shall include:
• Conduit replacement.
• Wiring replacement.
• Equipment replacement.
• Panel improvements.
• Safety improvements.
The Contractor shall coordinate with utility providers as necessary.
4.34 PROJECT EXCLUSIONS
The following items are specifically excluded:
• Parking Lot Improvements.
• Playground Improvements.
• Security Camera Systems.
• Access Control Systems.
• Public Wi-Fi Systems.
• Audiovisual Systems.
• Scoreboard Replacements.
• Athletic Lighting Replacements.
4.35 PROJECT CLEANUP
The Contractor shall maintain a clean work site throughout construction.
The Contractor shall remove debris on a regular basis.
4.36 FINAL RESTORATION
Upon completion, all disturbed areas shall be restored.
Restoration shall include:
• Grading.
• Sod.
• Seeding.
• Landscape restoration.
4.37 OWNER TRAINING
The Contractor shall provide training for City personnel on:
• Irrigation Systems.
• HVAC Systems.
• Building Systems.
• Warranty Procedures.
4.38 CLOSEOUT DOCUMENTS
The Contractor shall provide:
• As-Built Drawings.
• Warranty Documentation.
• Equipment Manuals.
• Operations Manuals.
• Maintenance Manuals.
4.39 WARRANTY
The Contractor shall provide a minimum one-year warranty on all labor, materials, equipment, and workmanship.
Manufacturer warranties exceeding one year shall be assigned to the City.
4.40 PROJECT COMPLETION
Substantial Completion shall be achieved within one hundred eighty (180) calendar days following issuance of the Notice to Proceed.
Final Completion shall be achieved within thirty (30) calendar days following Substantial Completion.
END OF SECTION 01210



SECTION 01250
PROPOSAL FORM
MOBLEY PARK REMODEL
DESIGN-BUILD REQUEST FOR PROPOSALS
CITY OF PORT WENTWORTH, GEORGIA
PROPOSER INFORMATION
Legal Name of Firm:

Business Address:


Telephone:

Email:

Primary Contact:

Georgia Contractor License Number:

Architect of Record:

Georgia Registration Number:

Engineer of Record:

Georgia Registration Number:

PROPOSAL CERTIFICATION
The undersigned, having carefully examined the Request for Proposals, Addenda, site conditions, and all Contract Documents for the Mobley Park Remodel Project, hereby proposes to furnish all labor, supervision, professional services, materials, equipment, permits, transportation, insurance, bonds, and incidentals necessary to complete the Work in accordance with the Contract Documents.
The undersigned certifies that all information contained within this proposal is true and correct.
PROPOSED CONTRACT AMOUNT
Lump Sum Design-Build Price:
$_________________________
DESIGN SERVICES BREAKDOWN
Architecture:
$_________________________
Engineering:
$_________________________
Permitting:
$_________________________
Other Design Services:
$_________________________
Total Design Services:
$_________________________
CONSTRUCTION COST BREAKDOWN
Site Improvements:
$_________________________
Athletic Field Improvements:
$_________________________
Irrigation Improvements:
$_________________________
Batting Cage Facility:
$_________________________
Restroom Building Renovation:
$_________________________
Announcer Building Renovation:
$_________________________
Concession Building Renovation:
$_________________________
Electrical Improvements:
$_________________________
General Conditions:
$_________________________
Contractor Contingency:
$_________________________
Total Construction Cost:
$_________________________
PROJECT DURATION
The undersigned agrees to achieve Substantial Completion within:
________________ Calendar Days
The proposed duration shall not exceed one hundred eighty (180) calendar days following issuance of the Notice to Proceed.
ADDENDA ACKNOWLEDGEMENT
The undersigned acknowledges receipt of the following Addenda:
Addendum No. _____ Date __________
Addendum No. _____ Date __________
Addendum No. _____ Date __________
Addendum No. _____ Date __________
NON-COLLUSION CERTIFICATION
The undersigned certifies that this proposal has been prepared independently and without collusion, fraud, or improper communication with any other proposer.
DEBARMENT CERTIFICATION
The undersigned certifies that neither the firm nor any principal associated with the firm has been suspended, debarred, or otherwise prohibited from contracting with any governmental agency.
AUTHORIZATION
I certify that I am authorized to submit this proposal on behalf of the proposer.
Company:

Authorized Signature:

Printed Name:

Title:

Date:

END OF SECTION 01250



SECTION 01350
DESIGN-BUILD AGREEMENT
MOBLEY PARK REMODEL
CITY OF PORT WENTWORTH, GEORGIA
THIS AGREEMENT is entered into this _____ day of __________________, 2026, by and between the CITY OF PORT WENTWORTH, GEORGIA, hereinafter referred to as the "Owner," and ____________________________________________, hereinafter referred to as the "Design-Build Contractor."
ARTICLE 1
PROJECT
The Contractor shall provide all professional services, design services, permitting, labor, supervision, materials, equipment, tools, transportation, testing, inspections, and incidentals necessary to complete the Mobley Park Remodel Project located at the 400 Block of Armadale Road, Port Wentworth, Georgia 31407.
The Work shall be performed in accordance with the Contract Documents.
ARTICLE 2
CONTRACT DOCUMENTS
The Contract Documents shall consist of:
1. Request for Proposals
2. Addenda
3. Contractor's Proposal
4. Statement of Qualifications
5. General Conditions
6. Supplemental Conditions
7. Scope of Work
8. Performance Bond
9. Payment Bond
10. Notice to Proceed
11. Approved Change Orders
12. Approved Design Documents
13. Approved Submittals
14. All documents incorporated by reference
These documents are incorporated into this Agreement as though fully set forth herein.
ARTICLE 3
CONTRACT AMOUNT
The Owner shall pay the Contractor the sum of:
$________________________________
("Contract Amount")
The Contract Amount shall include all costs necessary to complete the Work.
ARTICLE 4
CONTRACT TIME
The Contractor shall commence work upon issuance of the Notice to Proceed.
Substantial Completion shall be achieved within one hundred eighty (180) calendar days following issuance of the Notice to Proceed.
Final Completion shall be achieved within thirty (30) calendar days following Substantial Completion.
Time is of the essence.
ARTICLE 5
LIQUIDATED DAMAGES
The parties acknowledge that damages resulting from delayed completion are difficult to calculate.
Should the Contractor fail to achieve Substantial Completion within the Contract Time, the Contractor shall pay the Owner liquidated damages in the amount of Five Hundred Dollars ($500.00) for each calendar day beyond the Contract Time.
Liquidated damages may be deducted from amounts otherwise due to the Contractor.
ARTICLE 6
DESIGN RESPONSIBILITIES
The Contractor shall provide all design services required for completion of the project.
Design services shall include:
• Architectural Design
• Civil Engineering
• Structural Engineering
• Mechanical Engineering
• Electrical Engineering
• Plumbing Engineering
• Irrigation Design
All design documents shall be prepared under the supervision of professionals licensed in the State of Georgia.
ARTICLE 7
CONCEPTUAL DESIGN REVIEW
Within thirty (30) calendar days of Notice to Proceed, the Contractor shall submit a Conceptual Design Package.
The Conceptual Design Package shall include:
• Site Plan
• Architectural Elevations
• Material Selections
• Preliminary Irrigation Design
• Preliminary Grading Plan
• Construction Schedule
The City Manager shall serve as the approving authority for Conceptual Design submissions.
Final design shall not proceed until Conceptual Design approval is received.
ARTICLE 8
PERMITS
The Contractor shall obtain all permits, approvals, licenses, and inspections necessary to complete the Work.
The Contractor shall coordinate all regulatory approvals.
ARTICLE 9
PAYMENT PROCEDURES
The Contractor shall submit monthly Applications for Payment.
Applications shall include:
• Schedule of Values
• Percent Complete
• Stored Material Documentation
• Lien Waivers
• Supporting Documentation
The Owner shall review applications and process payments in accordance with Georgia law.
ARTICLE 10
RETAINAGE
The Owner may withhold retainage as permitted by Georgia law.
Retainage may be reduced or released upon satisfactory progress.
ARTICLE 11
CHANGES IN THE WORK
The Owner may direct changes in the Work.
Changes shall be documented through written Change Orders.
No adjustment to Contract Amount or Contract Time shall be valid unless approved in writing.
ARTICLE 12
INSURANCE
The Contractor shall maintain insurance throughout the duration of the project.
Minimum limits shall be:
Commercial General Liability
$1,000,000 Per Occurrence
$2,000,000 Aggregate
Automobile Liability
$1,000,000 Combined Single Limit
Workers Compensation
Statutory Limits
Employer's Liability
$1,000,000
Professional Liability
$1,000,000
Builder's Risk
Full Replacement Value
Certificates of Insurance shall be provided prior to commencement of work.
ARTICLE 13
PERFORMANCE BOND
The Contractor shall furnish a Performance Bond equal to one hundred percent (100%) of the Contract Amount.
ARTICLE 14
PAYMENT BOND
The Contractor shall furnish a Payment Bond equal to one hundred percent (100%) of the Contract Amount.
ARTICLE 15
WARRANTIES
The Contractor warrants that:
• Materials shall be new unless otherwise approved.
• Work shall be free from defects.
• Work shall comply with Contract requirements.
The warranty period shall be one (1) year following Final Acceptance.
ARTICLE 16
INDEMNIFICATION
To the fullest extent permitted by law, the Contractor shall indemnify, defend, and hold harmless the Owner, its elected officials, officers, employees, and agents from claims, damages, losses, liabilities, and expenses arising out of performance of the Work.
ARTICLE 17
DEFAULT
The Contractor shall be in default if the Contractor:
• Fails to supply sufficient labor.
• Fails to supply sufficient materials.
• Fails to maintain progress.
• Violates Contract requirements.
• Becomes insolvent.
• Abandons the Work.
ARTICLE 18
TERMINATION FOR CAUSE
If the Contractor defaults, the Owner may terminate the Agreement after written notice and opportunity to cure.
The Owner may complete the Work through others and recover associated costs.
ARTICLE 19
TERMINATION FOR CONVENIENCE
The Owner reserves the right to terminate the Agreement for convenience.
The Contractor shall be compensated for work properly completed through the termination date.
ARTICLE 20
DISPUTE RESOLUTION
The parties shall first attempt to resolve disputes through informal negotiations.
If unresolved, disputes shall proceed to mediation prior to litigation.
ARTICLE 21
GOVERNING LAW
This Agreement shall be governed by the laws of the State of Georgia.
Venue shall lie exclusively in Chatham County, Georgia.
ARTICLE 22
ENTIRE AGREEMENT
This Agreement constitutes the entire agreement between the parties.
No modification shall be effective unless executed in writing by both parties.
IN WITNESS WHEREOF, the parties have executed this Agreement on the dates indicated below.
CITY OF PORT WENTWORTH
By: __________________________________
Name: _______________________________
Title: ________________________________
Date: ________________________________
ATTEST:

CONTRACTOR
Company:

By:

Name:

Title:

Date:

END OF SECTION 01350



SECTION 01300
BID BOND
MOBLEY PARK REMODEL
KNOW ALL MEN BY THESE PRESENTS:
That we, ______________________________________, as Principal, and ______________________________________, as Surety, are held and firmly bound unto the City of Port Wentworth, Georgia, in the penal sum of five percent (5%) of the total proposal amount.
The Principal has submitted a proposal for the Mobley Park Remodel Design-Build Project.
If the Principal is awarded the Contract and executes the Agreement and furnishes the required bonds within the time specified, then this obligation shall be void.
Otherwise, the obligation shall remain in full force and effect.
Principal:

Surety:

Authorized Signature:

Date:

END OF SECTION 01300



PERFORMANCE BOND
MOBLEY PARK REMODEL
Bond No. ______________________
KNOW ALL MEN BY THESE PRESENTS:
That ______________________________________ as Principal and ______________________________________ as Surety are held and firmly bound unto the City of Port Wentworth, Georgia in the amount of one hundred percent (100%) of the Contract Amount.
The Principal has entered into a Design-Build Agreement for the Mobley Park Remodel Project.
The Surety guarantees faithful performance of the Contract.
If the Principal fully performs the Contract, this obligation shall be void.
Otherwise, the Surety shall remain liable under the terms of this Bond.
Principal:

Surety:

Attorney-in-Fact:

Date:

END OF PERFORMANCE BOND
PAYMENT BOND
MOBLEY PARK REMODEL
Bond No. ______________________
KNOW ALL MEN BY THESE PRESENTS:
That ______________________________________ as Principal and ______________________________________ as Surety are held and firmly bound unto the City of Port Wentworth, Georgia in the amount of one hundred percent (100%) of the Contract Amount.
The Principal shall promptly pay all laborers, suppliers, subcontractors, and material providers associated with the Work.
If such obligations are fully satisfied, this Bond shall be void.
Otherwise, this Bond shall remain in effect.
Principal:

Surety:

Attorney-in-Fact:

Date:

END OF PAYMENT BOND



SECTION 01400
NOTICE TO PROCEED
MOBLEY PARK REMODEL
CITY OF PORT WENTWORTH, GEORGIA
DATE: _______________________
TO:



PROJECT:
Mobley Park Remodel
400 Block Armadale Road
Port Wentworth, Georgia 31407
You are hereby notified to commence Work in accordance with the Design-Build Agreement dated _____________________.
The Contract Time of one hundred eighty (180) calendar days shall commence on _____________________.
Substantial Completion shall be achieved no later than _____________________.
Final Completion shall be achieved no later than _____________________.
The Contract Amount is:
$_____________________________________
CITY OF PORT WENTWORTH
By:

Name:

Title:

Date:

END OF SECTION 01400



ATTACHMENT A
DRUG FREE WORKPLACE CERTIFICATION
MOBLEY PARK REMODEL
The undersigned certifies that the proposer will provide a drug-free workplace by:
1. Publishing a statement notifying employees that unlawful manufacture, distribution, dispensing, possession, or use of a controlled substance is prohibited.
2. Establishing a drug-free awareness program.
3. Requiring employees to notify the employer of any criminal drug statute conviction occurring in the workplace.
4. Taking appropriate personnel action against employees who violate the policy.
The undersigned certifies compliance with the Georgia Drug-Free Workplace Act.
Firm:

Authorized Signature:

Printed Name:

Title:

Date:

NOTARY
State of _____________________
County of ___________________
Subscribed and sworn before me this _____ day of ________________, 20.
Notary Public

My Commission Expires:

END OF ATTACHMENT A
ATTACHMENT B
PROMISE OF NON-DISCRIMINATION
MOBLEY PARK REMODEL
The undersigned certifies that the firm shall not discriminate against any employee or applicant because of race, color, religion, sex, national origin, age, disability, or any other protected classification recognized by law.
The proposer agrees to comply with all applicable federal and state equal employment opportunity requirements.
Firm:

Authorized Signature:

Date:

END OF ATTACHMENT B
ATTACHMENT C
DEBARMENT CERTIFICATION
MOBLEY PARK REMODEL
The undersigned certifies that neither the firm nor any principal associated with the firm has been suspended, debarred, proposed for debarment, declared ineligible, or voluntarily excluded from participation in governmental contracting.
Firm:

Authorized Signature:

Date:

END OF ATTACHMENT C
ATTACHMENT D
NON-COLLUSION AFFIDAVIT
MOBLEY PARK REMODEL
The undersigned certifies that this proposal has been made independently and without collusion, consultation, communication, or agreement with any other proposer.
The undersigned further certifies that no attempt has been made to induce another party to submit or refrain from submitting a proposal.
Firm:

Authorized Signature:

Date:

NOTARY
State of _____________________
County of ___________________
Subscribed and sworn before me this _____ day of ________________, 20.
Notary Public

My Commission Expires:

END OF ATTACHMENT D
ATTACHMENT E
NO-BID STATEMENT
MOBLEY PARK REMODEL
Firm Name:

The undersigned has elected not to submit a proposal for the following reason(s):
☐ Insufficient Time
☐ Project Too Large
☐ Project Too Small
☐ Unable to Meet Schedule
☐ Scope Outside Expertise
☐ Other
Explanation:


Authorized Signature:

Date:

END OF ATTACHMENT E
ATTACHMENT G
LEGAL NOTICE
CITY OF PORT WENTWORTH, GEORGIA
REQUEST FOR PROPOSALS
MOBLEY PARK REMODEL
The City of Port Wentworth, Georgia is soliciting sealed proposals from qualified Design-Build Teams for the Mobley Park Remodel Project located at the 400 Block of Armadale Road, Port Wentworth, Georgia 31407.
The project generally consists of design, permitting, and construction services associated with athletic field improvements, irrigation systems, batting cage replacement, sidewalk replacement, building renovations, roofing replacement, architectural upgrades, and electrical improvements.
Proposal Schedule
Advertisement Date:
July 20, 2026
Mandatory Pre-Proposal Meeting:
July 27, 2026
11:00 A.M. EST
Port Wentworth City Hall
7224 Highway 21
Port Wentworth, Georgia 31407
Deadline for Questions:
July 31, 2026
Addenda Issued:
August 5, 2026
Proposal Due Date:
August 21, 2026
11:00 A.M. EST
Anticipated Award:
No Later Than August 31, 2026
Proposals shall be submitted to:
City of Port Wentworth
7224 Highway 21
Port Wentworth, Georgia 31407
The City reserves the right to reject any or all proposals, waive informalities, negotiate with the highest-ranked proposer, and award the contract in the best interest of the City.
END OF ATTACHMENT G
E-VERIFY CONTRACTOR AFFIDAVIT
MOBLEY PARK REMODEL
By executing this affidavit, the undersigned contractor verifies compliance with O.C.G.A. §13-10-91.
The contractor verifies that it is registered with and participates in the federal work authorization program commonly known as E-Verify.
Contractor Name:

E-Verify User Identification Number:

Date of Authorization:

Authorized Signature:

Printed Name:

Title:

Date:

NOTARY
State of _____________________
County of ___________________
Subscribed and sworn before me this _____ day of ________________, 20.
Notary Public

My Commission Expires:

END OF E-VERIFY AFFIDAVIT
image1.jpeg
ITY
=

STAND UP FOR AMERICA C!




